## Remediation Tracker
Remediation ID | Finding ID | Risk ID | Control ID | Asset ID | Finding / Issue | Remediation Action | Implementation Method | Priority | Status | Verification Method | Verification Result | Evidence Reference | Notes
REM-01 | F-01 | R-01 | CTL-01 | AST-002 | S3 public access protection was misconfigured. | Enable S3 public-access blocking and restore the intended secure bucket configuration. | Terraform secure configuration + AWS verification | High | Completed | Re-run the S3 detection check and verify the AWS bucket configuration. | PASS | Evidence/F-01-S3-Public-Access/ | Remediation was verified in the existing cloud lab.
REM-02 | F-02 | R-02 | CTL-02 | AST-003 | IAM policy granted excessive permissions. | Reduce the IAM policy to the required least-privilege permissions. | Terraform IAM policy configuration + AWS verification | Critical | Completed | Re-run the IAM detection check and verify the final IAM policy. | PASS | Evidence/F-02-IAM-Permissions/ | Remediation was verified in the existing cloud lab.
REM-03 | F-03 | R-03 | CTL-03 | AST-004 | Security Group permitted overly broad inbound access. | Restrict SSH/network access to the approved source range and required service. | Terraform Security Group configuration + AWS verification | High | Completed | Re-run the Security Group detection check and verify final inbound rules. | PASS | Evidence/F-03-Security-Group/ | Remediation was verified in the existing cloud lab.
REM-04 | F-04 | R-04 | CTL-04 | AST-002 | S3 encryption enforcement was misconfigured. | Configure/enforce S3 server-side encryption according to the secure baseline. | Terraform S3 configuration + AWS verification | High | Completed | Re-run the S3 encryption detection check and verify the bucket encryption configuration. | PASS | Evidence/F-04-S3-Encryption/ | Remediation was verified in the existing cloud lab.
REM-05 | F-05 | R-05 | CTL-05 | AST-005 | CloudTrail logging was disabled or not operating as intended. | Enable CloudTrail logging and restore the intended audit-logging configuration. | Terraform/CloudTrail configuration + AWS verification | High | Completed | Re-run the CloudTrail detection check, verify logging status, and review the relevant CloudTrail activity. | PASS | Evidence/F-05-CloudTrail/ | The existing lab also investigated the StopLogging event as part of the scenario.
REM-06 | GAP-09 |  |  |  | GRC evidence existed across the technical project but was not yet organized into a dedicated evidence structure. | Create evidence folders by finding and place the existing screenshots, detector output, remediation proof, and verification evidence into the appropriate folders. | Git repository evidence organization | Medium | Planned | Review each finding folder and confirm that evidence supports detection, remediation, and verification. | Pending | grc/Evidence/ | This is the next GRC implementation task.

## Read Me
Cloud Security Lab — GRC Remediation Tracker
Purpose | Tracks remediation actions from the five actual cloud findings and the remaining evidence-organization gap.
Why completed items are included | The technical lab already performed the remediation. This tracker formally records what was fixed, how it was implemented, and how the fix was verified.
Verification | A remediation is not considered complete merely because a configuration was changed. The tracker records a separate verification method and result.
Current next task | REM-06 organizes the existing technical evidence into the GRC Evidence folder.
Scope limitation | This is a practical remediation tracker for the AWS security lab. It does not represent an enterprise ticketing/change-management system.